# Implementation, Testing & Documentation Plan

Delivery playbook • Release 1.0 integrated core and advanced scope

Release 1.0 | Baseline 3.0 | 21 October 2026 | Status: Approved for implementation (supersedes Baseline 2.0)

# 1. Delivery principles

SRS v3, Architecture v3, ADR log v3 and the resolved Inconsistency Register are the sources of truth; Claude must explicitly identify any new contradiction before coding and record it as a new INC item instead of resolving it silently.

The approved Baseline 3.0 diagrams (01–05 .drawio) are the data and permission reference for the Prisma schema; any schema change updates the ERD and the cross-check in the same change.

Build vertical slices that exercise API, database, permission checks, and UI together; never mark mocked screens as complete.

Prioritize P0 security and functionality, then P1 advanced features; use a written gap list if time/credit runs short.

Avoid duplicated work: inspect repository state, implement only missing features, run focused tests then one final full regression.

# 2. Suggested delivery gates, 21 October–5 November

| Gate | Dates | Deliverable / pass condition |
| --- | --- | --- |
| G0 | Oct 21–22 | SRS v3, Architecture v3, ADR-001…020, resolved INC register and Baseline 3.0 draw.io diagrams approved; traceability report with TC-* IDs published. |
| G1 | Oct 22–24 | Monorepo + migrations (composite FKs, partial unique indexes) + APP/PLATFORM sessions + PlatformAdmin seed + tenant isolation tests + API skeleton. |
| G2 | Oct 24–27 | Workspace (invitation lifecycle, removal cascade, ownership transfer, timezone) / project / issues / permissions / comments incl. moderation, fully tested with UI. |
| G3 | Oct 27–30 | Kanban (Member status rule, PM ranking), backlog, sprint lifecycle incl. cancel and scope change, epics/subtasks, watchers, uploads. |
| G4 | Oct 30–Nov 2 | Dashboards, burndown, velocity, workload (workspace timezone), notification/outbox, scheduled jobs and platform admin. |
| G5 | Nov 2–5 | Security/accessibility QA, regression, seed demo, CI, deployment, screenshots and portfolio README. |

Dates are target checkpoints, not guarantees. Do not sacrifice authorization, tests, or honest completion reporting merely to meet dates.

# 3. Screen-to-function implementation order

| Slice | Front-end | Backend + quality evidence |
| --- | --- | --- |
| Identity | Register/login/verify/reset/profile | Session model, rate limit, CSRF, auth integration tests |
| Tenancy | Create/select workspace, invites (resend/revoke/accept), members/settings, ownership transfer | Tenant policy, owner invariant, removal cascade, email-match acceptance, cross-tenant isolation tests |
| Projects | Project dashboard/list/detail/settings/members | Project CRUD, archive, role tests |
| Issues | List, issue detail, form, hierarchy, comments (edit/delete/moderate), attachments, watchers | Issue schemas, hierarchy matrix, key allocator, assignee eligibility, activity, upload authorization |
| Board and sprint | Kanban/backlog/sprint planning, cancel, closure | Status vs rank permissions, version handling, one active sprint, one open sprint per issue, snapshots |
| Analytics | Project/overview reports | Deterministic aggregates, fixtures, report reconciliation |
| Notifications | Bell/inbox read/unread and platform admin pages | Outbox delivery, dedupe, watcher fan-out, PlatformAdmin guard, tenant protection |

# 4. Test strategy

| Test type | Minimum target |
| --- | --- |
| Unit | Role policy helpers, field allow-lists, hierarchy matrix, issue state rules, unique key allocation, sprint math, timezone day boundaries, analytics selectors. |
| Integration | Every mutating endpoint authorization + validation; cross-tenant leakage; composite-FK violations; invitation lifecycle; removal cascade; transaction conflict handling; status codes per ADR-015. |
| E2E | Register/invite -> project -> issue -> board -> sprint -> report; multiple roles and denied routes. |
| UI accessibility | Keyboard navigation, forms and board fallback, contrast, labeling and focus management. |
| Security | Session fixation/logout, APP vs PLATFORM session separation, CSRF, IDOR, attachment ACL, rate limiting, secrets, audit trails. |
| Operational | Fresh DB migrations and seed, Docker start, CI reproducibility, backup/restore runbook. |
| Traceability | Every FR and AC mapped to TC-* test IDs in Traceability Report v3; CI test names carry the TC ID; release gate requires all TC-* passing or listed as a known gap. |

# 5. Definition of done per module

Functional behavior matches its numbered FR; permissions enforced in API and frontend discoverability.

Zod schemas, DB constraints and transaction boundaries documented; no mock-only success states.

Automated tests for successful, invalid, unauthorized, cross-tenant and conflict paths, asserting the status codes and error codes defined in ADR-015.

Loading/empty/error states and responsive behavior demonstrated at 390px, 768px and desktop widths.

OpenAPI routes, sample requests, README and architecture updated; no credentials or secrets committed.

Evidence recorded: tests run, screenshots, known limitations, files modified, migration impact.

# 6. Required documentation deliverables

| Document | Purpose |
| --- | --- |
| 01 SRS v3 | Numbered functional/non-functional requirements and release criteria |
| 02 Architecture v3 | Components, security, data entities (22), composite keys, route inventory, status-code contract |
| 03 Delivery plan v3 | Gates, tests, release checklists and Claude discipline |
| 04 01_system_workflow.drawio | Lifecycle states, authorized operations, exception paths |
| 05 02_user_flows.drawio | Role-based journeys, major screens, failure and recovery |
| 06 03_database_erd.drawio | Entity attributes, PK/FK, unique constraints, cardinalities |
| 07 PERMISSION_MATRIX_v3.csv + 04_role_permissions.drawio | Resource-by-role operation policy and project/tenant edge cases |
| 08 OpenAPI 3.1 (.yaml) | HTTP API contract including DTO/errors |
| 09 Test plan + report | Trace IDs to tests and passed/failed evidence |
| 10 Deployment runbook | Environment, migrations, secrets, backup, rollback and monitoring |
| 11 Portfolio README + case study | Live demo, architecture decisions, screenshots, challenges and tradeoffs |
| 12 05_navigation_sitemap.drawio | Pages, routes, role-restricted screens, desktop/mobile navigation |
| 13 ADR log v3 | ADR-001…ADR-020 decisions, rationale and consequences |
| 14 Inconsistency Register v3 | INC-01…INC-27 with resolution and affected artifacts |
| 15 Traceability Report v3 | Requirement → entity → API → user flow → test case |

# 7. Claude Cloud Session credit-saving discipline

Start each session with task scope, explicit touched modules, acceptance criteria and stop conditions.

Ask Claude to inspect existing docs/code and summarize gaps before modifying; do not blindly regenerate scaffolds or redesign the schema.

One session per domain slice; do not run a full repository suite on every minor change.

Run focused tests continuously and full end-to-end regression at a release gate; log actual command outputs.

Require a concise end-of-session handoff: completed, tests, changed files, migrations, blockers, and next task.

Never let the assistant create destructive migrations, mutate production, seed non-demo DBs, or deploy without explicit permission.

Avoid verbose terminal dumps and token-heavy documentation reprinting; update precise sections.

# 8. Go/no-go release checklist

☐ No cross-tenant data leakage in automated tests

☐ All P0 + requested P1 features complete or transparently marked incomplete

☐ No high/critical security findings unresolved

☐ Fresh installation and migrations verified

☐ Role-based E2E journeys passed

☐ Sprint reports reconcile with data and historical snapshots

☐ Demo dataset fictional, stable and easy to reset

☐ Hosted link, screenshots, diagrams, OpenAPI and GitHub README working

☐ Every TC-* in the Traceability Report passing, or listed as a known gap

☐ ERD, Prisma schema and Architecture §4 in sync (automated cross-check green)

# 9. Major risks and mitigations

| Risk | Mitigation |
| --- | --- |
| 15-day delivery window | Freeze combined scope; prioritize complete vertical slices; track remaining credit. |
| Over-designed authorization | Two-layer role model, field allow-lists and status codes are fixed in ADR-002/008/015; test matrix generated from PERMISSION_MATRIX_v3.csv. |
| ERD divergence from code | ERD is generated first and then synchronized with Prisma migrations on each schema change. |
| Report errors | Specify metric math, build fixture-based tests and reconcile outputs. |
| Context/credit waste | Use compact session handoffs, targeted file reads and gated regression. |
| Appearance over functionality | Require working endpoints and E2E proof for portfolio screenshots. |
| Baseline 3.0 scope growth | Changes limited to resolving INC-01…27 (watchers, PlatformAdmin, composite keys, timestamps); no further features without a new INC/ADR entry. |